## Slide 1: Regional Strategy
Ministry for the Environment Waste Minimisation Fund
“Small Community Collective Biosolids Strategy – Rural Lower North Island”
Led by LEI and ESR/CIBR
Funded for 3 years
Aims: develop a collective biosolids strategy and use programme in the lower North Island.
Partners:
  Manawatu District Council;
  Rangitikei District Council;
  Tararua District Council;
  Whanganui District Council;
  Masterton District Council;
  Kapiti Coast District Council;
  Horowhenua District Council;
  Ruapehu District Council, and
  Horizons Regional Council.

## Slide 2: Project workplan
Task 01: Project management (Hamish Lowe)
Task 02: Project Governance Group
  Provide support to Project Manager
  Identify and manage internal Council issues
  Aid dissemination of project information within individual Councils
  Group to consist of each partner council and a representative from LEI and ESR
    Can we form this group today????

## Slide 3: Stage 1 Gap analysis
Task 1a: What is happening now?
Desk top study
  Review available information
  Data will be collated to generate a regional picture of the volumes and types of sludge that require management.
  Starting now!!!
Who are the key Council contacts?

## Slide 4
Task 1b Site visits and field investigations
  Site visit and field work to determine sludge volumes and characteristics where data is not available
  Early next year
Task 1c Gap analysis report
  Collate all information from desk top study and field work into final report
  Output: Final report sent to partner councils and MfE
  April 2017

## Slide 5: Stage 2 Opportunities to Work Together
Identify regional capacity and areas where Councils could work together.
Develop matrix where the various contributions can be shown from each partner.
Scope and potential for working together will be described in a Memorandum of Understanding (MoU).
Due date: July 2017

## Slide 6: Stage 3 Community and Stakeholder Engagement Framework
Develop an iwi engagement plan
  Due date: January 2017
Workshop with local iwi and Hapū; short list of preferred scenarios for biosolids
  Due date: April 2017
Draft Engagement Framework circulated to partner councils and external peer reviewers.
  Due date: December 2017
Engagement Framework finalised and published
  Due date: May 2018

## Slide 7: Stage 4 Scenario Evaluation
Using background information collected in Stages 1, 2 and 3 - develop ‘straw men’ scenarios of what collective and regional biosolids management might look like.
Due date: October 2017

## Slide 8: Stage 5 Draft Strategy
The background work, including scenarios and engagement, will form draft strategy.
Workshop - evaluate and debate the potential range of collective biosolids management scenarios and options.
Draft strategy - short list of preferred scenarios for managing biosolids and forward action plan, including a ratified framework for engagement with stakeholders.
Due date: October 2017

## Slide 9: Stage 6 Biosolids treatment and processing trials
Develop field trial design
  Due Date: January 2017
Site preparation
  Due date: April 2017
Collect sludges from at least 3 different districts.
Set-up field trial
  Due date: July 2017
Monitor trial
  Due date: October 2017

## Slide 10: What do we need from you today?
Form Governance Group – representative from each partner Council
Key contacts at each Council:
  to provide information for Gaps Analysis – work starting now!
  to be involved in field trial design – work starting now!